## Instructions
General Instructions
• The Program Development and Validation Tracker is an Excel workbook that must be used to plan and track the development, validation, and approval of programs used to generate Analysis and Reporting deliverables. Usage of the tracker is required for all deliverables in scope for BARDS SOP B-S004. • This is an exception-based tracking tool. Instead of documenting step by step activity, only exceptions to required activities are captured. Entering a status of "complete" indicates all required activities were completed and exceptions have been documented, if noted in the Exceptions tab. • A single Program Development and Validation Tracker workbook is used to track all programs/macros for a deliverable (e.g., CSR, interim, investigator brochure, annual IND, etc.). • For detailed information about the content of and how to complete this Program Development and Validation Tracker workbook, refer to: Definitions for Tab Names below, instructions at the top of the Plan and Track tab and Exceptions tab, and required B-S004 training courses.
Definitions of Tabs in this Workbook
Yellow tabs: Indicates tabs that must be completed to comply with B-S004 procedures
Green tabs: Are for Reference Only and are to be used to complete information in the Plan and Track and Exceptions tabs.
Tab Name | Definition of each Tab
Instructions | Lists each workbook tab and a general definition for each of each tab in this workbook.
Plan and Track | Mandatory Tab: Used to plan validation (assign categories, describe testing; assign testers) and track status of development and validation activities.
Exceptions | Mandatory Tab: used to document exceptions to requirements in "Required Activities" tab. Requirement author, Developer, Independent Validator, Double Programmer or Customer assigned to activity with exception is required to document exceptions on this tab and provide the business need and/or alternative process followed.
Required Activities | Reference Tab: Lists Mandatory Activities for each Validation Procedure Step in B-S004 (e.g. Requirements/Specifications, Developer Testing, Double Programming, etc. ). The process step is comprised of multiple activities identified by a unique identifier. Each identifier indicates a particular activity. For example: - each Requirements/Specifications activity begins with "rs", followed by a unique number such as rs01, rs02; - each Developer Testing activity begins with "dt", followed by a unique number such as dt01, dt02.
Validation Category Definitions | Reference Tab: Provides guidance for assigning program categories
Template Revision History | Reference Tab: Used by the Process Team to capture versions of this template including date and changes made

## Plan and Track
Overall Program Status **NOT ENTERABLE Auto-populated based on Status Columns I, L, P, and T | Program Name: Enter program name; each program occupies one row in the Tracker. Round Number: **If blank, "1" is assumed. It should be used when a validated program is modified after it is used in production. An example is a program used for interim analysis, modified and used again after final database lock. Description: Enter brief description of the program. Also, if a program requires multiple testing scenarios, note the use of a complex validation plan in this field. Store the plan in appropriate folder for the computing platform using the naming convention "program name-Validation Plan". Program Validation Category: Refer to "Validation Category Definitions" tab of this workbook. Note: A previously validated program may have a different category from the original version of the program when the program has no or minor modifications. Minor modifications are those that do not involve a change to the logic of the program or analysis algorithm. Minor modifications do not affect the actual data content contained in an analysis dataset or displayed in a TLF. Some examples of minor modifications include such things as; updates to Titles and Footnotes, adding comments to the Program Header, and formatting revisions. THIS TEMPLATE WILL PRE-POPULATE COLUMNS G - T, dependent on the testing requirements. For example, Program Category 4 requires only Developer Testing, therefore NA will be populated automatically for Independent and Double Programming related columns. Program Subfolder: is the relative path of the subfolder where the program resides. (e.g. /pgmsetup, /macrolib) Original Program Location:** REUSED-Program Validation Category 4 Programs ONLY** This should ONLY be completed for previously validated programs which have been copied and reused with no or minor modifications. Enter the protocol deliverable location where original Validation materials can be found. For Example (e.g.MK9999-001, V999-001). Note: When entering an Original Program Location, "Requirements/Specifications" fields (columns H-J) will be set to N/A; this can be overwritten if necessary (i.e. additional Specifications were created). | [5 empty] | Requirements/Specifications Who: ISID of Specification Author Status: Complete (C) Not Started (N) or In Progress (I) Entering "C" indicates that all required activities were completed and any relevant exceptions noted. Refer to the Required Activities tab for details. |  |  | Developer Testing Who: ISID of program developer Status: Complete (C) Not Started (N) or In Progress (I) Entering "C" indicates that all required activities were completed and any relevant exceptions noted. Refer to the Required Activities tab for details. NOTE: Although "NA" is an option on the "Status" drop down list- the response "NA" is NOT a valid option to select for Developer Testing. |  |  | Double Programming: Who: ISID of double programmer Double Programming Description: For datasets, indicate if entire dataset will be programmed or specify a subset of key variables. For TLFs, all (not format) should be verified. Status: Complete (C) Not Started (N) or In Progress (I) Entering "C" indicates that all required activities were completed and any relevant exceptions noted. Refer to the Required Activities tab for details. |  |  |  | Independent Review/Testing: Who: ISID of Independent Reviewer Independent Review/Testing Description: is populated by the assigned reviewer/tester to briefly document the planned review/testing they will do. Status: Complete (C) Not Started (N) or In Progress (I) Entering "C" indicates that all required activities were completed and any relevant exceptions noted. Refer to the Required Activities tab for details. |  |  |  | Customer Review: ONLY for programs requiring Customer Review/Approval Who: ISID of Customer Reviewer Status: For programs requiring Customer Approval, "Approved" is entered by the assigned customer to indicate completed review and approval. "Not Approved" is entered by the assigned customer to indicate revisions required. Refer to the Required Activities tab for details. If Status is blank, "N/A" is assumed. |  |  |  | Flag to denote programs being included in a submission package. Select "Y" if included in submission package. If blank, assume "N"
[7 empty] | Exception Number indicates the unique activity identifier which was not followed. Activity Identifiers are found in the Required Activities tab of this workbook. |  |  | Exception Number indicates the unique activity identifier which was not followed. Activity Identifiers are found in the Required Activities tab of this workbook. |  |  | Exception Number indicates the unique activity identifier which was not followed. Activity Identifiers are found in the Required Activities tab of this workbook. |  |  |  | Exception Number indicates the unique activity identifier which was not followed. Activity Identifiers are found in the Required Activities tab of this workbook. |  |  |  | Exception Number indicates the unique activity identifier which was not followed. Activity Identifiers are found in the Required Activities tab of this workbook.
Overall Program Status | Program Name | Round Number** | Description | Program Validation Category | Program Subfolder | Original Program Location ** | Who | Status | Exception Number | Who | Status | Exception Number | Who | Double Programming Description | Status | Exception Number | Who | Independent Review/Testing Description | Status | Exception Number | Who | Customer Review Description | Status | Exception Number | Submission Package Deliverable Y, N or Blank: | Comments / Notes (As needed) | Formula below:
Complete | baamr_risk_badge | v0.1.0 | Function to declare badges of risk category of a package | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_sdlc_badge | v0.1.0 | Function to declare developmental stage of a package | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved
Complete | baamr_validation_badge | v0.1.0 | Function to declare badge of validation steps in the package | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_codecov_badge | v0.1.0 | Function for code coverage badges | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_build_badge | v0.1.0 | Function to build badges | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_check | v0.1.0 | Function to check the compliance of a BAAMR internal standard package | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Not Started | baamr_check | v0.1.1 | Function to check the compliance of a BAAMR internal standard package | 3 | [8 empty] | NA | NA | NA | NA | [10 empty] | Not Started
Complete | ps_check | v0.1.0 | Function to check compliance of a BAAMR project specific package | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Not Started | ps_check | v0.1.1 | Function to check compliance of a BAAMR project specific package | 3 | [8 empty] | NA | NA | NA | NA | [10 empty] | Not Started
Complete | baamr_build_site | v0.1.0 | Function to generate static HTML documentation for BARDS internal standard package | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Not Started | baamr_build_site | v0.1.1 | Function to generate static HTML documentation for BARDS internal standard package | 3 | [8 empty] | NA | NA | NA | NA | [10 empty] | Not Started
Complete | ps_build_site | v0.1.0 | Function to generate static HTML documentation for BARDS project specific package | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_deploy_site | v0.1.0 | Function to deploy BARDS internal standard package site | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_path_to_pc | v0.1.0 | Function for CPI access folder for local PC | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_path_to_server | v0.1.0 | Function for CPI access folder for BAAMR server | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_setwd | v0.1.0 | Function to set working directory based on current computing environment | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_use_ps_template | v0.1.0 | Create project specific package template wizard | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_use_std_template | v0.1.0 | Create internal standard R package template wizard | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | baamr_rename | v0.1.0 | Function for rename | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Not Started | baamr_rename | v0.1.1 | Function for rename | 3 | [8 empty] | NA | NA | NA | NA | [10 empty] | Not Started
Complete | is_baamr | v0.1.0 | Function to check whether current environment is BAAMR server | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | is_merckpc | v0.1.0 | Function to check whether current environment is Merck PC | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | mosc_add_copyright | v0.1.0 | Function for adding copyright in each R file | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete
Complete | sys_isid | v0.1.0 | Functions to extract ISID based on current user's environment | 4 |  |  | zhuyal | C |  | zhuyal | C |  | NA | NA | NA | NA | NA | NA | NA | NA | zhanyilo | N/A | approved |  |  |  | Complete

## Exceptions
Program Name | Round Number | Exception Number | Exception Description | Exception Justification (if applicable)
Enter Program Name from column A of Plan and Track Tab | Enter Round Number from column B of Plan and Track Tab | Enter each unique activity identifier (e.g. dt04) in this column. If needed, list multiple exceptions separated by a coma. | Describe why the required activity was not completed, for example: - Required activity was not applicable - program was not utilizing any statistical methods. - Evidence/documents not named or stored in accordance with standard convention; Indicate alternative name and/or location. | If the following Exception(s) (ind06, db07) was noted because a final deliverable was created prior to the completion of required testing, a risk assessment should be completed and the justification noted in this column. All required activities should be completed retrospectively and details should be documented in this column (i.e. Program delivered on 01/Feb/2017- but Independent Review Testing was completed on 05/Feb/2017 due to critical deadline).

## Required Activities
Procedure Step From B-S004 | Procedure Description (Description of the required Activity) | Required Activities to Save Evidence (Evidence must be saved in accordance with designated Computing Platform rules) | Required Activities for ALL Macros and Programs (INCLUDING calling programs) | Additional Required Activities for Macros and Programs (EXCEPT for calling programs) | Additional Functional Area Specific Activities (Checks to be completed only by the specific functional area noted)
Requirements/ Specifications | Customer documents requirements for the deliverable. Developer completes the programming specifications in the appropriate template for the request type (e.g. TLF, ADaM dataset, non-Adam dataset, macro, etc.). | When an exception to the required evidence saved occurs, note each unique activity identifier (e.g. rs02) for that exception in the Exceptions tab. rs01: Final version of Requirements/Specification document saved according to standard directory structure of computing platform rs02: Requirements/Specification document follows naming convention to include Program Name rs03: Documented Requirements/Specification Completion in Plan and Track Tab of this workbook. Note: Requirements/Specifications for SDTM programming are generated by GCDS and may not follow BARDS naming and storage conventions. | NA | NA | NA
Developer Testing | Developer testing is conducted by the developer to ensure that the program meets the documented requirements and successfully executes in accordance with the specifications. For TLF programs using input metadata or parameters, developer testing should include validating that the inputs (metadata or parameter values) align with the specs. | When an exception to the required evidence saved occurs, note each unique activity identifier (e.g. dt02) for that exception in the Exceptions tab. dt01: Input data and metadata dt02: Testing program(s) used for developer testing dt03: Output logs, lst file, TLFs and datasets created dt04: Evidence saved according to Standard Directory Structure dt05: Documented Completion of developer testing in plan and track tab of this document Note: Programs stored in the "jobaide" folder of the Global Macro Library (\\bardsar- prod\standards\jobaide) are not fully validated. When utilized for a protocol deliverable, the study team must assign the program a validation category and validate accordingly. Note: Category 4 Calling Programs signoff may reside in the A&R Grid. Note: Evidence not required to be saved for Calling Programs Note: If multiple test case scenarios in test plan, evidence of each scenario tested should be saved. | When an exception to the required activities occurs, note each unique activity identifier (e.g. dt06) for that exception in the Exceptions tab. dt06: The developer must ensure that there is data to test all applicable data scenarios (i.e. include regular data and missing data). dt07: If needed, the developer should review literature for unfamiliar or novel statistical analysis When development is complete, the developer should review: dt08: Log for errors, warnings and uninitialized variables. dt09: Output to ensure expected output was generated dt10: If used, metadata inputs align with specifications . | When an exception to the required additional activities occurs, note each unique activity identifier (e.g. dt16) for that exception in the Exceptions tab. dt11: Review output for issues with format and content dt12: Code and output aligns with the final requirements/specifications including merges, sorting and merging variables and rounding of intermediate steps. dt13: Program/macro runs correctly and an accurate number of observations and variables are retained dt14: Program/macro header is complete and accurate (if required for program type) dt15: Code aligns with programming practices dt16: No duplicate records created dt17: All expected variables are populated dt18: Effective and understandable comments were used in body of programming code Additional checks to consider, if applicable: dt19: Statistical methods are valid and accurate dt20: Hard coding has an approved exception dt21: Dataset for repeats of values in match merge variables are correct dt22: Verify unnecessary output was suppressed dt23: Data manipulations were manually tested on a subset of data (e.g. data transformations, manipulation algorithms, derived analysis variables and population subsetting routines) dt24: Variations in optional execution (macros, variables, parameters) were tested | Standard Macros: dtS1: Checked all variations in optional execution (macros, variables, parameters) dtS2: If needed, verified correct generation of bulletproof error checks dtS3: Verified program follows macro development guidelines- B-S004.ER39 dtS4: All revisions to the program are listed in the revisions section of the header dtS5: Checked that round and date in top of macro match that of the dev. folder dtS6: All macro names within the program are in lower case dtS7: Verified user documentation is complete, correct and up-to-date. dtS8: Verified sample package runs correctly and is up-to-date. dtS9: Tested program on all applicable OS (SAS V9.3 on Unix) dtS10: Verified program is stored in the correct format on all applicable OS dtS Note: Standards Programmer- Evidence is not required to be saved by the Standards Developer for Developer Testing of Template Programs in the Standard Jobaide Folder.
Double Programming | Double programming is conducted to ensure the content of analysis datasets and TLFs is accurate. This tester follows the program specifications to develop code independently and checks that their output matches the output of the developer. While coding, the validation programmer does not consult with the developer or refer to the actual programming code of the developer. | When an exception to the required evidence saved occurs, note each unique activity identifier (e.g. dt02) for that exception in the Exceptions tab. db01: Description of planned double programming in Plan and Track Tab of this workbook db02: Input data and metadata db03: Testing programs used for double programming and/or to compare output db04: Output logs, lst file, TLFs and datasets created by double programmer db05: Evidence that output of double programmer aligns with output of developer db06: Documented Double Programming Completion in Plan and Track Tab of this workbook. db07: Final deliverable created prior to completion of required testing Note: If multiple data scenarios are listed in test plan, evidence of each scenario tested should be saved. Note: Programs stored in the "jobaide" folder of the Global Macro Library (\\bardsar- prod\standards\jobaide) are not fully validated. When utilized for a protocol deliverable, the study team must assign the program a validation category and validate accordingly | Exceptions to required checks must be captured in exceptions tab of this document using the unique activity identifier (e.g. db09) for that exception in the Exceptions tab. The double programmer must: db08: independently create and execute code using requirement specification as reference db09: confirm that the output they created for the datasets, variables or TLFs defined in Plan and Track tab of this workbook matches the output from the developer Note: Format of TLFs does not need to be matched, just counts | NA
Independent Review/Testing | Independent review/testing is conducted by a person other than the developer to ensure that the program created by the developer meets the documented requirements. This may include activities such as: ·Review of code to ensure the program aligns with the specification ·Execution of code for some/all scenarios ·Execution of code and review of results ·Parallel programming of a piece of the code ·Testing using data from multiple therapeutic areas or studies ·Call Metadata setup checks (Accenture/Cytel standards checks their own work) – ID has separate tracking sheet to make sure this is done. | When an exception to the required evidence saved occurs, note each unique activity identifier (e.g. ind01) for that exception in the Exceptions tab. ind01: Description of planned Independent Review/Testing in Plan and Track Tab of this workbook. ind02: Documented Independent Review/Testing completion in Plan and Track Tab of this workbook. Additional evidence to save, if applicable ind03: Input data and metadata ind04: Testing programs created by independent reviewer/tester ind05: Output logs, lst file, TLFs and datasets created by independent reviewer/tester ind06: Final deliverable created prior to completion of required testing Note: If multiple data scenarios are listed in test plan, evidence of each scenario tested should be saved. Note: Programs stored in the "jobaide" folder of the Global Macro Library (\\bardsar- prod\standards\jobaide) are not fully validated. When utilized for a protocol deliverable, the study team must assign the program a validation category and validate accordingly | Exceptions to required checks must be captured in exceptions tab of this document using the unique activity identifier (e.g. ind09) for that exception in the Exceptions tab. ind07: The independent tester/reviewer must conduct all checks that are defined in Plan and Track tab of this workbook. | NA
Customer Review [OPTIONAL] | Customer review is conducted prior to finalizing programs. Customer reviewer should ensure they are comfortable with the accuracy and format of each deliverable. | When an exception to the required evidence saved occurs, note each unique activity identifier (e.g. cr01) for that exception in the Exceptions tab. During validation planning, any programs which require customer review should be identified and documented in the Plan and Track tab of this workbook. For those programs: cr01: Customer Approval must be captured in the Plan and Track tab of this workbook. Note: For programs not requiring formal customer approval, no evidence is required. | Exceptions to required checks must be captured in exceptions tab of this document using the unique activity identifier (e.g. cr02) for that exception in the Exceptions tab. cr02: Customer Reviewer reviews output provided by Developer to ensure the output (format and content) aligns with requirements. | NA | Standards crs1:Standards Requires Customer Approval and must be captured in the "Plan and Track" tab HTA: crh1: Customer review conducted on Production Data ESD: Customer Review procedure is never applicable for ESD statistical analysis programs when the customer is the developer, i.e. statistician.
Quality Control (QC) Setup/Output [OPTIONAL] | QC is used to ensure that setup of a validated report is correct and that output aligns with expectations. Examples include metadata setup checks and review of counts to ensure they align across tables. QC is not required to be Tracked. You may add columns to the end of the Plan and Track Tab if you wish to document this activity. | None | None | NA | NA
Dry Run [OPTIONAL] | A Dry Run is execution of a planned set of validated programs using production data (generally blinded to treatment) in the Test Environment to ensure the programs and macros function as expected when actual trial data is used. Dry Run is not required to be Tracked. You may add columns to the end of the Plan and Track Tab if you wish to document this activity. | None | NA | NA | NA

## Validation Category Definitions
Category Number | Required Testing | Program Validation Category Description | Functional Area Guidelines
1 | Developer Testing Double Programming Independent Review/Testing | Most critical - programs with important analysis (e.g. primary efficacy) as well as complex statistical algorithms needing independent testing.
2 | Developer Testing Double Programming | Critical programs with important analysis (e.g. primary efficacy, analysis dataset programs) | RWE (PE): Critical programs where safety results are presented outside the company. To be used for PASS or safety analyses in which the results will be presented externally, programs that generate an analytic dataset or produce results for a primary objective. For these types of studies, all remaining programs will go through independent review.
3 | Developer Testing Independent Review/Testing | Programs with complex statistical algorithms needing independent testing. | ESD: to be used in cases where the ESD statistician determines that Independent testing/review is necessary, i.e. review of SAS Proc code for running a complex statistical model with complicated contrasts, or ensuring that a composite endpoint in an analysis data set has been derived properly. The statistician should be very specific about what needs to be reviewed/tested when filling out the Independent Review/Testing Description column on the Plan and Track tab. RWE(PE): Programs where results are presented outside the company. To be used based on the type of project where results are presented externally (e.g. PASS or safety analyses, non-PASS/non-safety analyses). For non-PASS/non-safety analyses in which the results will be presented externally, programs that generate an analytic dataset or produce results for a primary objective. What is done for Independent review\testing must ensure the quality of the program being reviewed.
4 | Developer Testing | Non-critical programs without complex algorithms | ESD: Programs written by the Statistician to support analysis are considered non-critical and are therefore Category 4 programs. Standards: Programs developed and stored in the "jobaide" folder of the Standards Library (\\bardsar-prod\standards\jobaide) require minimal developer testing by the Standards Developer. See Note box below for all other functional areas besides Standards utilizing jobaide programs. RWE(PE): Non-critical programs where results are not presented outside the company.
SPECIAL NOTATIONS: Note: All analysis datasets (ADaM) programs require a minimum of a Validation Category 2. Note: Other types of program checks/testing such as Customer Review, QC and dry runs of programs are not associated with program categories. When formal sign off for these activities are required by a functional area, they should be tracked in the Plan and Track tab of this workbook. Note: Any Jobaide programs (stored in the "jobaide" folder of the Standards Library (\\bardsar-prod\standards\jobaide)) utilized for a protocol deliverable must be assigned a program validation category and be validated accordingly.

## Template Revision History
Template Version Number | Effective Date | Revision Description
1 | Dec. 31, 2016 | Initial Document
1.1 | Mar. 13, 2017 | [Instructions] tab: - Revised and enhanced content and formatting for clarity [Plan and Track] tab: - Updated instructions for all columns for clarity - Added column A for overall program status - Added customer review description in column W - Corrected logic connect to program category and requirement specification so that only when program category 4 is selected and orginial program location is not null, the requirement specifications will defaul to NA. [Exceptions] tab: - Updated format and instructions for clarity [Required Activities] tab: - Deviation codes were revised and enhanced for clarity - Added rows for Specifications/Requirements and Customer Review -Additional Functional Area Specific Activities (column F) added for HTA, ESD and Standard Macros [Validation Category Definitions] tab: - Functional Area Guidelines (column D) added for ESD Validation Tracker Workbook was optimized for enhanced performance.
5.2 | 2018-02-28 | Updated Required Activities Tab; dt03, ind05, and db04 to say - Output logs, lst file, TLFs and datasets created - KMD
5.3 | 2018-04-13 | Updated the Validation Category Definitions tab with RWE (PE) function are specific notes- KMD
5.4 | 2018-06-12 | Added NOTE for SDTM SP- to Required Activities tab- Requirements/Specifications Column C
5.5 | 2018-10-31 | "Required Activities" tab- for Dev Testing- Updated Note under Column C-Evidence is not required to be saved for Calling Programs only. "Required Activities" tab- for Dev Testing- Added Functional Area (dtS NOTE) note in Dev Testing- for Standards Programmers only "Validation Categeory Definitions" tab: Added "Analysis Dataset Programs" to Validation Category 2- Double Programming. All analysis datasets should be double programmed "Validation Categeory Definitions" tab: Removed Funtional Area Note from "Validation Catetory" tab Category 4-"ESD: Statistical analysis programs are non-critical programs, and are Category 4". All Analysis Programs require atleast a Category 2 assignment.
5.6 | 2018-12-12 | Updated Required Activities Tab; dt, ind and db with the following NOTE: Programs stored in the "jobaide" folder of the Global Macro Library (\\bardsar- prod\standards\jobaide) are not fully validated. When utilized for a protocol deliverable, the study team must assign the program a validation category and validate accordingly
5.7 | 2019-12-18 | Updated the Validation Category Definitions tab with ESD functional area specific notes for Validation Category 4- KMD
5.8 | 2019-09-27 | Added a Note under Developer Testing regarding the option "NA" . Developer Testing should be completed for all programs- irrespective of the validation category. NOTE: Although "NA" is an option on the "Status" drop down list- the response "NA" is NOT a valid option to select for Developer Testing